## Sheet1
Table 2: Timeline of activities and expected outputs of TCG Working Groups, 2017-2018
[11 empty] | Working progress |  | TCG approval
[11 empty] | Consultation |  | Advocacy
| Activities and expected outputs | 2017 | [5 empty] | 2018
|  | Q2 |  |  | Q3 | Q4 |  | Q1 | Q2 |  |  | Q3 |  | Q4
WG1 | 3 indicators | Develop methodology |  |  |  | Consultation |  | TCG approval | [5 empty] | Approval by IAEG on global indicators
| 4 indicators |  | Develop methodology |  |  |  |  | Consultation |  | TCG approval
| Additional indicators/areas | [5 empty] | Identify & agree | Develop methodology | Consultation |  |  | TCG approval
| Additional indicators/areas | [7 empty] | Identify & agree |  | Develop methodology |  | Consultation
WG2 | Capacity development framework document |  | Develop the framework |  |  |  | Populate | Validate the framework | Identify gaps |  | Advocacy
WG3 | Documents of data flow, data realease calendar, and terminology |  |  | Produce documents |  |  |  | Develop methodology
| Suggestions on validation process | [6 empty] | Develop methodology
| Formulate a strategy to identify alternative data sources in cases of missing globally comparable data | [6 empty] | Formulate a strategy

## Sheet2
Working progress | TCG approval
Consultation | Advocacy